TaskFlow Pro Phase-Wise Implementation Plan Small Tasks Breakdown · March 2026 · v2.0 (Phases 1–7)

| Phase 1 Foundation & Auth Week 1–2 | Phase 2 Project Management Week 3–4 | Phase 3 Task Management Week 5–6 | Phase 4 Comments & Notifications Week 7–8 |
| --- | --- | --- | --- |

| Phase 5 Dashboard & UI Polish Week 9–10 | Phase 6 DevOps & QA Week 11–12 | Phase 7 Performance & Load Testing Week 13–14 |
| --- | --- | --- |

## Phase Summary

| Phase | Scope | Duration | Key Deliverable |  |
| --- | --- | --- | --- | --- |
| Phase 1 | Foundation & Auth | Week 1–2 | Working login + JWT backend |  |
| Phase 2 | Projects & DB | Week 3–4 | Project CRUD + schema migrations |  |
| Phase 3 | Task Management | Week 5–6 | Full task lifecycle |  |
| Phase 4 | Comments, Notifs, Activity | Week 7–8 | Collaboration features |  |
| Phase 5 | Dashboard & UI Polish | Week 9–10 | Dashboard + responsive UI |  |
| Phase 6 | DevOps & QA | Week 11–12 | CI/CD + tests + monitoring |  |
| Phase 7 | Performance & Load Testing | Week 13–14 | All 4 tools · All 4 test types | NEW |

# 1.  Project Overview

TaskFlow Pro is an enterprise-grade collaborative task management platform built with Java 21 / Spring Boot 3 on the backend and React 18 / MUI on the frontend, deployed on AWS EKS with PostgreSQL. This document breaks the MVP (v1.0) delivery into 7 focused phases, each shipping a working, testable vertical slice of functionality. Phase 7 adds a comprehensive performance and load testing layer covering four tools and four test strategies.

## Tech Stack at a Glance

| Layer | Technology |
| --- | --- |
| Backend | Java 21 · Spring Boot 3.x · Spring Security · JPA/Hibernate · Flyway |
| Frontend | React 18 · Vite · Redux Toolkit · Material UI v5 |
| Database | PostgreSQL 16 · UUID PKs · Flyway versioned migrations |
| Auth | JWT (HS512) · Access token 15 min · Refresh token 7 days · BCrypt strength 12 |
| DevOps | Docker · Kubernetes (EKS) · Helm · Terraform · GitHub Actions CI/CD |
| Monitoring | Prometheus · Grafana · Structured JSON logs · Spring Actuator |
| Perf Testing | k6 · Apache JMeter · Gatling · Locust (Python) · InfluxDB · Grafana |

PHASE 1 Foundation & Authentication · Week 1 – 2

Goal: Runnable backend + frontend skeleton with JWT authentication end-to-end. After this phase a developer can register, log in, get a token, and refresh it.

## 1.1  Backend — Database & Migration Setup

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| B1-01 | Create Flyway migration V1: users table (UUID PK, email UNIQUE, role, is_active, timestamps) | V1__create_users_table.sql | Add index on email |
| B1-02 | Create Flyway migration V8: refresh_tokens table (token, user_id FK, expires_at, is_revoked) | V8__create_refresh_tokens_table.sql | Unique index on token |
| B1-03 | Configure application.yml: datasource, Flyway, JPA ddl-auto=validate, HikariCP pool | resources/application.yml | Profile: dev & prod |
| B1-04 | Implement User JPA entity + UserRepository (findByEmail) | model/User.java · repository/UserRepository.java | Spring Data JPA |
| B1-05 | Implement RefreshToken entity + repository | model/DomainModels.java | is_revoked soft-delete |

## 1.2  Backend — JWT Security

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| B1-06 | Implement JwtTokenProvider: generate access token (15min HS512) + refresh token (7 days) | security/JwtTokenProvider.java | Store secret in env var |
| B1-07 | Implement JwtAuthFilter: extract Bearer token, validate, set SecurityContext | security/JwtAuthFilter.java | Stateless — no session |
| B1-08 | Configure SecurityConfig: permit /auth/**, protect all other routes, CORS, CSRF disabled | config/SecurityConfig.java | Spring Security 6.x |
| B1-09 | Implement AuthService: register (BCrypt pw hash), login (validate + generate tokens), refresh, logout | service/AuthService.java | Strength 12 BCrypt |
| B1-10 | Implement AuthController: POST /auth/register, /auth/login, /auth/refresh, /auth/logout | controller/AuthController.java | Return 201/200/204 |
| B1-11 | Implement GlobalExceptionHandler: 400 validation, 401 token errors, 409 conflict, 500 | exception/GlobalExceptionHandler.java | Standard error JSON |
| B1-12 | Write unit tests for AuthService (register, login, refresh, duplicate email) | test/AuthServiceTest.java | Mockito · JUnit 5 |

## 1.3  Frontend — Project Scaffold & Auth UI

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| F1-01 | Initialise Vite + React 18 project; install MUI, Redux Toolkit, React Router, Axios | frontend/package.json | npm create vite@latest |
| F1-02 | Setup Redux store + authSlice (token, user, loading, error state) | store/index.js · store/slices/authSlice.js | Persist token in localStorage |
| F1-03 | Create api.js Axios instance: base URL, Authorization header interceptor, 401 token refresh interceptor | services/api.js | Auto-refresh on 401 |
| F1-04 | Implement authService.js: register(), login(), refreshToken(), logout() calling backend | services/authService.js | Wrap Axios calls |
| F1-05 | Build LoginPage (/login): email + password fields, error alert, loading spinner, redirect on success | pages/LoginPage.jsx | MUI TextField + Button |
| F1-06 | Build RegisterPage (/register): full name, email, password + confirm, strength indicator, terms checkbox | pages/RegisterPage.jsx | Password strength bar |
| F1-07 | Implement ProtectedRoute: redirect to /login if no token; wrap authenticated routes in App.jsx | components/auth/ProtectedRoute.jsx · App.jsx | React Router v6 |
| F1-08 | Build shared Layout + NavBar: logo, nav links, notification bell placeholder, user avatar menu | components/shared/Layout.jsx · NavBar.jsx | Responsive drawer |

### Definition of Done

- POST /auth/register returns 201 with user object

- POST /auth/login returns access token + refresh token

- POST /auth/refresh rotates tokens correctly

- Invalid credentials return 401 with error body

- Frontend login form submits, stores token, redirects to /dashboard placeholder

- Protected routes redirect to /login when unauthenticated

- Unit tests pass with >= 80% coverage on AuthService

PHASE 2 Project Management · Week 3 – 4

Goal: Users can create, view, update, and archive projects. Project membership (invite by email, role assignment) is functional.

## 2.1  Backend — Database Migrations

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| B2-01 | Migration V2: projects table (name, description, status, visibility, owner_id FK, timestamps) | V2__create_projects_table.sql | Indexes on owner_id, status |
| B2-02 | Migration V3: project_members table (project_id, user_id, role, joined_at) + UNIQUE constraint | V3__create_project_members_table.sql | Composite unique index |

## 2.2  Backend — Project API

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| B2-03 | Project JPA entity + ProjectRepository (findByOwnerOrMember, findByStatus) | model/Project.java · repository/ | Spring Data Specifications |
| B2-04 | ProjectMember JPA entity + repository | model/DomainModels.java | Composite PK or UUID |
| B2-05 | ProjectService: createProject (auto-add creator as MANAGER), getProjects (paginated), getById | service/ProjectService.java | Check visibility/membership |
| B2-06 | ProjectService: updateProject (name/desc/status), archiveProject (soft-delete status=ARCHIVED) | service/ProjectService.java | Only MANAGER/ADMIN |
| B2-07 | ProjectService: addMember (lookup by email, assign role), removeMember, updateMemberRole | service/ProjectService.java | Validate not already member |
| B2-08 | ProjectController: GET/POST /projects, GET/PUT/DELETE /projects/{id} | controller/ProjectController.java | Paginated response wrapper |
| B2-09 | ProjectController: GET/POST /projects/{id}/members, DELETE /projects/{id}/members/{userId} | controller/ProjectController.java | Role guard via @PreAuthorize |
| B2-10 | Request/Response DTOs: CreateProjectRequest, ProjectResponse, MemberResponse, PagedResponse | dto/request/Requests.java · dto/response/Responses.java | Validation annotations |

## 2.3  Frontend — Projects UI

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| F2-01 | Create projectService.js: getProjects(), createProject(), updateProject(), deleteProject(), getMembers(), addMember() | services/projectService.js | Axios calls to /api/v1/projects |
| F2-02 | Create projectsSlice in Redux: projects list, selected project, loading/error state | store/slices/projectsSlice.js | Async thunks |
| F2-03 | Build ProjectListPage (/projects): grid of ProjectCards, status filter chips, search field, + New Project button | pages/ProjectListPage.jsx | 3-col responsive grid |
| F2-04 | Build ProjectCard component: name, description truncated, status badge, progress bar, member avatars, kebab menu | components/projects/ProjectCard.jsx | MUI Card |
| F2-05 | Build CreateProjectModal: name (required), description, visibility toggle — submit calls createProject() | components/projects/CreateProjectModal.jsx | MUI Dialog |
| F2-06 | Build ProjectDetailPage (/projects/:id): sticky header with name, status, member avatars, + Add Task button, tabs (Board ¦ List ¦ Activity) | pages/ProjectDetailPage.jsx | Tab routing |
| F2-07 | Build ProjectMembersPanel: list current members with roles, invite by email form, remove member | components/projects/ProjectMembersPanel.jsx | MANAGER only actions |

### Definition of Done

- Authenticated user can create a project and see it in the list

- Project owner auto-assigned as MANAGER

- Members can be invited by email; roles enforced (MANAGER can add/remove, MEMBER cannot)

- Archiving a project hides it from the Active filter

- Frontend Project List and Detail pages render with correct data

PHASE 3 Task Management · Week 5 – 6

Goal: Full task CRUD within projects — create, assign, update status/priority/due-date, delete. Board view and List view both functional.

## 3.1  Backend — Tasks

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| B3-01 | Migration V4: tasks table (title, description, status, priority, due_date, assignee_id, reporter_id, project_id, position, tags[]) | V4__create_tasks_table.sql | Composite index (project_id, status) |
| B3-02 | Task JPA entity with @ElementCollection for tags array, enum mappings for Status/Priority | model/Task.java | PostgreSQL TEXT[] mapping |
| B3-03 | TaskRepository: findByProjectId (with filters), findByAssigneeId, findDueSoon (due_date < now+24h) | repository/TaskRepository.java | Spring Data + @Query |
| B3-04 | TaskService: createTask (set reporter = caller, trigger notification to assignee) | service/TaskService.java | Validate project membership |
| B3-05 | TaskService: getTasksByProject (status/priority/assignee filters, paginated), getTaskById | service/TaskService.java | Membership check on private |
| B3-06 | TaskService: updateTask (title/desc/priority/dueDate/tags — full PUT), only assignee/reporter/manager | service/TaskService.java | Log activity on change |
| B3-07 | TaskService: updateTaskStatus (PATCH /status) — validate allowed transition, log activity | service/TaskService.java | INVALID_STATUS_TRANSITION error |
| B3-08 | TaskService: reassignTask, deleteTask (MANAGER/ADMIN only, cascade to comments) | service/TaskService.java | Soft or hard delete |
| B3-09 | TaskController: GET/POST /projects/{id}/tasks, GET/PUT/DELETE /tasks/{id}, PATCH /tasks/{id}/status | controller/TaskController.java | Role guards |
| B3-10 | Task DTOs: CreateTaskRequest, UpdateTaskRequest, TaskResponse, TaskSummaryResponse | dto/ | @NotBlank, @Size validations |
| B3-11 | Implement /users/me GET (current user profile) + PUT (update fullName, avatarUrl) endpoints | controller/UserController.java | Needed by task assignee display |

## 3.2  Frontend — Task Board & Forms

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| F3-01 | Create taskService.js: getTasks(), createTask(), updateTask(), updateTaskStatus(), deleteTask() | services/taskService.js | Axios wrapping all task endpoints |
| F3-02 | Create tasksSlice: tasks by status map, selected task, CRUD operations as async thunks | store/slices/tasksSlice.js | Normalise by taskId |
| F3-03 | Build BoardView: 4 columns (TODO / IN PROGRESS / IN REVIEW / DONE), column headers with task count, + Add Task inline | components/tasks/BoardView.jsx | Horizontal scroll on mobile |
| F3-04 | Build TaskCard: priority colour strip, title, tags (up to 3 + overflow), due date (red if overdue), assignee avatar, comment count | components/tasks/TaskCard.jsx | Click → TaskDetailPage |
| F3-05 | Build CreateTaskDialog: title, description (textarea), priority selector, assignee dropdown (project members), due date picker, tags chip input | components/tasks/CreateTaskDialog.jsx | MUI Dialog |
| F3-06 | Build ListView: MUI DataGrid with sortable columns — Priority, Title, Assignee, Status chip, Due Date, Created | components/tasks/ListView.jsx | Column sorting |
| F3-07 | Build TaskDetailPage (/tasks/:id): breadcrumb, inline-editable title, priority chip, status dropdown with validation, description edit, sidebar with assignee/reporter/dueDate/tags/activity | pages/TaskDetailPage.jsx | 70/30 split desktop |
| F3-08 | Implement optimistic UI for task status change: update Redux state first, revert on API error + toast | components/tasks/TaskCard.jsx | Error snackbar on revert |
| F3-09 | Build MyTasksPage (/my-tasks): filtered to assigneeId = me, same Board/List toggle | pages/MyTasksPage.jsx | Reuse BoardView/ListView |

### Definition of Done

- Tasks created in a project appear in TODO column of the board

- Status transitions TODO → IN_PROGRESS → REVIEW → DONE work; invalid transitions return 422

- Priority, assignee, due date, tags all editable from Task Detail page

- List view sortable; board view shows correct column grouping

- Deleting a project cascades to delete its tasks

- My Tasks page shows only tasks assigned to current user

PHASE 4 Comments, Notifications & Activity · Week 7 – 8

Goal: Collaboration features — task comments, in-app notifications, and activity audit feed all working end-to-end.

## 4.1  Backend — Comments

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| B4-01 | Migration V5: comments table (content, task_id FK, author_id FK, is_edited, timestamps) | V5__create_comments_table.sql | Index on task_id + created_at |
| B4-02 | Comment JPA entity + CommentRepository (findByTaskIdOrderByCreatedAtAsc) | model/DomainModels.java · repository/ |  |
| B4-03 | CommentService: addComment (post → notify assignee + reporter), editComment (author only), deleteComment (author or MANAGER) | service/CommentService.java | Log COMMENT_ADDED activity |
| B4-04 | CommentController: GET/POST /tasks/{id}/comments, PUT /comments/{id}, DELETE /comments/{id} | controller/CommentController.java | Return 201 / 200 / 204 |
| B4-05 | Comment DTOs: CreateCommentRequest, CommentResponse with author UserSummary | dto/ |  |

## 4.2  Backend — Notifications

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| B4-06 | Migration V6: notifications table (type, message, is_read, user_id, task_id, project_id, created_at) | V6__create_notifications_table.sql | Partial index on (user_id, is_read=false) |
| B4-07 | Notification JPA entity + NotificationRepository (findByUserIdAndIsRead, countUnread) | model/DomainModels.java · repository/ |  |
| B4-08 | NotificationService: createNotification() internal method — called by TaskService, CommentService | service/NotificationService.java | Types: TASK_ASSIGNED, COMMENT_ADDED, STATUS_CHANGED |
| B4-09 | NotificationService: markAsRead(id), markAllAsRead(userId) | service/NotificationService.java |  |
| B4-10 | NotificationController: GET /notifications (paginated, ?isRead filter), PATCH /notifications/{id}/read, PATCH /notifications/read-all | controller/NotificationController.java | Include unreadCount in response |
| B4-11 | Add @Scheduled due-date reminder job: query tasks with due_date = tomorrow, create DUE_DATE_REMINDER notifications | service/NotificationService.java | @Scheduled(cron) daily |

## 4.3  Backend — Activity Log

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| B4-12 | Migration V7: activities table (action, entity_type, entity_id, actor_id, project_id, task_id, old_value, new_value, metadata JSONB, created_at) | V7__create_activities_table.sql | Indexes on project_id, task_id, created_at |
| B4-13 | Activity JPA entity + ActivityRepository (findByProjectId, findByTaskId, ordered by createdAt DESC) | model/DomainModels.java · repository/ |  |
| B4-14 | ActivityService: logActivity() — called internally from TaskService/CommentService on every state change | service/ActivityService.java | Actions: TASK_CREATED, STATUS_CHANGED, ASSIGNED, COMMENT_ADDED, etc. |
| B4-15 | ActivityController: GET /projects/{id}/activities, GET /tasks/{id}/activities (paginated) | controller/ActivityController.java | Latest first |

## 4.4  Frontend — Comments, Notifications & Activity

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| F4-01 | Build CommentSection in TaskDetailPage: CommentList (avatar, name, timestamp, content, edit/delete own), CommentForm (textarea + submit) | components/tasks/CommentSection.jsx | Poll for new comments every 30s |
| F4-02 | Create commentService.js and notificationService.js | services/ | Axios wrappers |
| F4-03 | Build NotificationBell in NavBar: badge showing unreadCount, click → NotificationDropdown | components/shared/NavBar.jsx | Poll /notifications every 60s |
| F4-04 | Build NotificationDropdown: scrollable list of notifications, click → navigate to task, Mark All Read button | components/notifications/NotificationDropdown.jsx | 380px panel desktop, full-screen mobile |
| F4-05 | Build ActivityFeed component (reusable): avatar + action text + timestamp, used on TaskDetailPage sidebar and ProjectDetailPage Activity tab | components/shared/ActivityFeed.jsx | Infinite scroll or load more |
| F4-06 | Wire Activity tab in ProjectDetailPage to GET /projects/{id}/activities | pages/ProjectDetailPage.jsx |  |
| F4-07 | Add notificationsSlice to Redux: unreadCount, notifications list, mark read actions | store/slices/notificationsSlice.js |  |

### Definition of Done

- Posting a comment creates a notification for assignee and reporter

- Assigning a task creates a TASK_ASSIGNED notification for the assignee

- NavBar bell badge updates with unread count; clicking a notification navigates to the task

- Mark all read clears the badge

- Activity feed shows correct actor, action, old/new values for all task changes

- Due-date reminder job creates notifications 24 hours before deadline

PHASE 5 Dashboard, Profile & UI Polish · Week 9 – 10

Goal: Dashboard with summary widgets, user profile management, responsive polish across all screens, and accessibility compliance.

## 5.1  Backend — Dashboard & Profile

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| B5-01 | Add GET /dashboard/summary endpoint: returns myTaskCounts (by status), dueThisWeek count, activeProjects count, unreadNotifCount | controller/DashboardController.java | Single aggregation query for perf |
| B5-02 | Add GET /tasks/my-tasks (filter by assigneeId = me, paginated) convenience endpoint | controller/TaskController.java | Reuse existing TaskService |
| B5-03 | PUT /users/me — update fullName + avatarUrl; PUT /users/me/password — verify currentPassword before update | controller/UserController.java | Return 200 / 204 |
| B5-04 | Add rate limiting filter on /auth/login (10 req/15min) and /auth/register (5 req/1hr) using Bucket4j or custom servlet filter | config/SecurityConfig.java or RateLimitFilter.java | Return 429 with retryAfter |
| B5-05 | Add OpenAPI/Springdoc dependency + config: expose /swagger-ui.html, /v3/api-docs; add @Operation annotations on all controllers | pom.xml + config/ | springdoc-openapi-starter-webmvc-ui |

## 5.2  Frontend — Dashboard & Profile

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| F5-01 | Build DashboardPage (/dashboard): 4 stat cards (My Tasks, Due Soon, Active Projects, Unread Notifications) from /dashboard/summary | pages/DashboardPage.jsx | Skeleton loading state |
| F5-02 | Build StatCard component: icon, label, value, optional trend indicator | components/dashboard/StatCard.jsx | MUI Card |
| F5-03 | Build MyTasksWidget: MUI DataGrid (5 rows) showing title, project, status chip, priority chip, due date | components/dashboard/MyTasksWidget.jsx | Click row → task detail |
| F5-04 | Build RecentActivityWidget on dashboard: last 10 events across all user projects (avatar + action + time) | components/dashboard/RecentActivityWidget.jsx | Poll or on-mount fetch |
| F5-05 | Build MyProjectsGrid on dashboard: up to 6 project cards with progress bar — completedTasks / totalTasks | components/dashboard/MyProjectsGrid.jsx | See all → /projects |
| F5-06 | Build ProfilePage (/profile): Personal Info section (fullName edit, email read-only, avatar upload placeholder), Change Password section | pages/ProfilePage.jsx | PUT /users/me + /password |
| F5-07 | Add Sidebar navigation: NavItems for Dashboard, Projects, My Tasks, Profile; icon-only on tablet, expanded on desktop, Drawer on mobile | components/shared/Layout.jsx · NavBar.jsx | MUI Drawer + List |
| F5-08 | Update App.jsx routing: all authenticated routes under Layout with Sidebar | src/App.jsx | React Router nested routes |
| F5-09 | Audit and fix all MUI breakpoint behaviours per UI/UX spec | All page components | Chrome DevTools breakpoint test |
| F5-10 | Add ARIA labels to all icon buttons, status chips, notification bell (aria-label, aria-live for badge), dialog role + focus trap | All components | WCAG 2.1 AA |
| F5-11 | Add Skip to main content link as first focusable element; visible focus rings on all interactive elements | components/shared/Layout.jsx | Keyboard-only navigation test |
| F5-12 | Add loading skeletons (MUI Skeleton) to Dashboard, Project List, Task Board during data fetch | All data-fetching pages | UX: no layout shift |
| F5-13 | Add toast/snackbar system (MUI Snackbar) for success/error feedback on all mutations | components/shared/ToastProvider.jsx | 3-second auto-dismiss |

### Definition of Done

- Dashboard loads all widgets with real data; stat counts are accurate

- Profile page updates name and password successfully

- App is fully keyboard-navigable; no focus traps outside dialogs

- Board view scrolls horizontally on mobile; sidebar collapses to drawer

- All mutations show success or error feedback toast

PHASE 6 DevOps, Testing & Monitoring · Week 11 – 12

Goal: Production-grade CI/CD pipeline, comprehensive test coverage, Docker/Kubernetes deployment, and observability stack fully operational.

## 6.1  Testing

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| T6-01 | Write integration tests for all AuthController endpoints using @SpringBootTest + Testcontainers (real PostgreSQL) | test/integration/ | Register, login, refresh, logout flows |
| T6-02 | Write unit tests for TaskService: create, update, status transitions (valid + invalid), delete, membership checks | test/java/com/taskflow/ | Mockito mocks |
| T6-03 | Write unit tests for CommentService, NotificationService, ActivityService | test/java/com/taskflow/ | Verify notification created on comment |
| T6-04 | Write integration tests for ProjectController, TaskController, CommentController via MockMvc | test/integration/ | Test 401/403 guards |
| T6-05 | Write Playwright E2E tests: register → login → create project → create task → update status → add comment → verify notification | tests/e2e/playwright/tests/taskflow.spec.ts | Headless Chromium |
| T6-06 | Write k6 load test: 500 concurrent users hitting GET /projects and POST /tasks, validate P95 < 300ms | tests/performance/k6-tests/ | k6 run with summary report |
| T6-07 | Achieve >= 80% line coverage on backend; add JaCoCo plugin to pom.xml and fail build if below threshold | pom.xml | mvn verify -Pcoverage |
| T6-08 | Add frontend component tests with Vitest + React Testing Library for LoginPage, TaskCard, BoardView, NotificationBell | frontend/src/__tests__/ | npm test |

## 6.2  Docker & Local Dev

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| D6-01 | Finalise backend Dockerfile: multi-stage (Maven builder → Eclipse Temurin 21 JRE), non-root user, HEALTHCHECK | backend/Dockerfile · infra/dockerfiles/Dockerfile.backend |  |
| D6-02 | Finalise frontend Dockerfile: node build stage → nginx:alpine serve stage, nginx.conf with SPA fallback | frontend/Dockerfile · infra/dockerfiles/Dockerfile.frontend |  |
| D6-03 | Update docker-compose.dev.yml: backend + frontend + postgres + prometheus + grafana services, volumes, env_file | infra/docker/docker-compose.dev.yml | One command local stack |
| D6-04 | Add Flyway migration scripts V1–V9 to backend resources and verify they run cleanly on fresh DB via compose | backend/src/main/resources/db/migration/ | V9 = all indexes |
| D6-05 | Create setup.sh: checks Docker installed, pulls images, runs compose, seeds demo data | scripts/setup.sh | README quick-start |

## 6.3  CI/CD — GitHub Actions

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| CI6-01 | backend-ci.yml: trigger on PR/push to main — checkout, set up Java 21, mvn test + JaCoCo report, fail on coverage < 80% | .github/workflows/backend-ci.yml | Upload coverage to Codecov |
| CI6-02 | frontend-ci.yml: trigger on PR/push — node setup, npm ci, npm run lint, npm test, npm run build | .github/workflows/frontend-ci.yml | Upload build artifact |
| CI6-03 | e2e-tests.yml: trigger on main merge — spin up docker-compose, wait for health, run Playwright, upload trace on failure | .github/workflows/e2e-tests.yml | Playwright HTML report artifact |
| CI6-04 | deploy.yml: on main merge + CI pass — build & push Docker images to ECR, kubectl rolling update on EKS (backend + frontend) | .github/workflows/deploy.yml | Zero-downtime rolling deploy |
| CI6-05 | Store secrets in GitHub Secrets: JWT_SECRET, DB_URL, DB_PASSWORD, AWS credentials, ECR registry URL | GitHub repo settings | Never commit secrets |

## 6.4  Kubernetes & Monitoring

| # | Task | Files / Area | Notes |
| --- | --- | --- | --- |
| K6-01 | Review/update backend-deployment.yaml: 2 replicas, HPA (min 2 max 10, CPU 70%), liveness + readiness probes on /actuator/health | infra/kubernetes/backend-deployment.yaml | RollingUpdate strategy |
| K6-02 | Review/update frontend-deployment.yaml + ingress.yaml: TLS termination, HTTPS redirect, host routing | infra/kubernetes/ | cert-manager for TLS |
| K6-03 | Configure Prometheus scraping: add annotations to backend pod for /actuator/prometheus endpoint | monitoring/prometheus/prometheus.yml | 15s scrape interval |
| K6-04 | Create Grafana dashboards: API latency (P50/P95/P99), error rate, JVM heap/GC, DB connection pool, active users | monitoring/grafana/dashboards/ | Import JSON dashboard |
| K6-05 | Add structured JSON logging with MDC correlation ID (traceId) to all controller and service methods | backend src/ | Logback JSON encoder |
| K6-06 | Verify Terraform prod config: EKS cluster, RDS PostgreSQL (Multi-AZ), VPC subnets, security groups, IAM roles | terraform/environments/prod/main.tf | terraform plan before apply |

### Definition of Done

- All backend unit + integration tests pass; JaCoCo reports >= 80% coverage

- E2E Playwright test runs headlessly in CI and passes

- k6 load test shows P95 API response < 300ms at 500 concurrent users

- GitHub Actions CI runs on every PR; deploy workflow pushes to EKS on main merge

- Prometheus scraping backend metrics; Grafana dashboards show live API latency and error rate

- docker-compose up --build runs the full local stack with one command

PHASE 7 Performance & Load Testing · Week 13 – 14 ¦ All Environments

Goal: Validate that TaskFlow Pro meets its SLA targets under real-world traffic. Cover four complementary strategies — Load, Stress, Spike, and Soak — using k6, JMeter, Gatling, and Locust (Python). Every critical API path is exercised, thresholds are enforced in CI, and HTML/JSON/Grafana reports are produced automatically.

## 7.0  Tool Overview & Responsibility Matrix

Each tool has a primary role. Running all four catches both protocol-level and scenario-level regressions, and gives the team flexibility across developer preferences.

| Tool | Primary Role | Test Types Covered | Language | CI Output |
| --- | --- | --- | --- | --- |
| k6 | Smoke / Load / Spike / Thresholds | Load · Stress · Spike | JavaScript (ES6) | JSON + Grafana Cloud |
| JMeter | Realistic browser-like scenarios, CSV user data | Load · Soak | XML DSL + Groovy | HTML Dashboard + JTL |
| Gatling | High-concurrency stress & developer-friendly DSL | Stress · Load | Scala / Kotlin DSL | HTML Simulation Report |
| Locust | Exploratory stress + developer scripts | Stress · Spike · Soak | Python | HTML + CSV + Grafana |

## 7.1  Global Performance Targets & SLA Thresholds

All tools enforce the following thresholds. A breach fails the CI build.

| Metric | P50 Target | P95 Target | Error Rate | Throughput |
| --- | --- | --- | --- | --- |
| POST /auth/login | < 100 ms | < 250 ms | < 0.5 % | > 200 rps |
| GET /projects (paginated) | < 80 ms | < 200 ms | < 0.5 % | > 300 rps |
| GET /projects/:id/tasks | < 100 ms | < 300 ms | < 1 % | > 250 rps |
| POST /projects/:id/tasks | < 150 ms | < 400 ms | < 1 % | > 150 rps |
| PATCH /tasks/:id/status | < 120 ms | < 350 ms | < 1 % | > 150 rps |
| GET /notifications (paginated) | < 80 ms | < 200 ms | < 0.5 % | > 200 rps |
| GET /dashboard/summary | < 150 ms | < 400 ms | < 1 % | > 100 rps |
| POST /tasks/:id/comments | < 150 ms | < 400 ms | < 1 % | > 100 rps |

## 7.2  k6 — Load, Stress & Spike Tests

k6 is the primary tool for automated threshold enforcement in the CI pipeline. Scripts are written in ES6 JavaScript and output JSON + Grafana Cloud metrics.

| # | Task | Tool | Test Type | File / Area | Notes |
| --- | --- | --- | --- | --- | --- |
| PT-K6-01 | Create k6 smoke test (5 VUs, 30 s): hit /auth/login, GET /projects, GET /projects/:id/tasks — verify 200 status and latency thresholds pass before heavier suites run | k6 | Load | tests/performance/k6/smoke.js | Run on every PR |
| PT-K6-02 | Create k6 load test: 500 concurrent VUs ramping 0→500 over 2 min, hold 5 min, ramp down — target endpoints: auth, projects CRUD, task CRUD, dashboard. Enforce P95 < 300 ms, error rate < 1% | k6 | Load | tests/performance/k6/load_test.js | T6-06 extension |
| PT-K6-03 | Create k6 stress test: ramp from 500 to 2 000 VUs in 5-VU steps every 30 s — identify the VU count at which P95 exceeds 1 s or error rate breaks 5%; record breaking point in report | k6 | Stress | tests/performance/k6/stress_test.js | Find ceiling |
| PT-K6-04 | Create k6 spike test: baseline 100 VUs for 2 min → instant jump to 1 500 VUs for 60 s → drop back to 100 VUs. Measure recovery time (time to return to P95 < 300 ms after spike) | k6 | Spike | tests/performance/k6/spike_test.js | Recovery SLA < 30 s |
| PT-K6-05 | Create k6 auth flow scenario: register new user → login → refresh token → logout. Run at 200 VUs for 3 min. Verify token rotation correctness, 401 rate < 0.1% | k6 | Load | tests/performance/k6/auth_flow.js | JWT correctness |
| PT-K6-06 | Create k6 board scenario: login → GET /projects → GET tasks (board) → PATCH task status → POST comment. Weighted realistic mix: 60% reads, 30% status updates, 10% comments | k6 | Load | tests/performance/k6/board_scenario.js | End-to-end flow |
| PT-K6-07 | Create k6 notification spike: trigger 1 000 concurrent task assignments in 5 s (burst write) → immediately GET /notifications for all users — verify notification delivery lag < 2 s | k6 | Spike | tests/performance/k6/notification_spike.js | Fan-out test |
| PT-K6-08 | Configure k6 thresholds block globally: http_req_duration p(95)<300, http_req_failed<0.01, http_reqs>100 — export results as JSON; add k6-to-junit converter for CI JUnit XML | k6 | Load | tests/performance/k6/config/thresholds.js | CI gate |
| PT-K6-09 | Add k6 GitHub Actions workflow (k6-load.yml): run smoke on PR, run full load suite on main merge; upload JSON summary + trend to Grafana Cloud via K6_CLOUD_TOKEN secret | k6 | Load | .github/workflows/k6-load.yml | Grafana Cloud |
| PT-K6-10 | Create k6 executor options file: use ramping-arrival-rate executor for throughput-based testing (target 300 rps sustained) — separate from VU-based scripts | k6 | Stress | tests/performance/k6/rps_test.js | Arrival-rate mode |

## 7.3  Apache JMeter — Load & Soak Tests

JMeter provides realistic browser-like HTTP/1.1 sessions with CSV-driven user data, cookie management, and detailed HTML dashboard reports. Ideal for long soak runs and complex multi-step scenarios.

| # | Task | Tool | Test Type | File / Area | Notes |
| --- | --- | --- | --- | --- | --- |
| PT-JM-01 | Create JMeter test plan (TaskFlowPro.jmx): Thread Group → CSV Data Set Config (100 pre-seeded users from users.csv) → HTTP Cookie Manager → HTTP Header Manager (Authorization: Bearer ${token}) | JMeter | Load | tests/performance/jmeter/TaskFlowPro.jmx | CSV auth |
| PT-JM-02 | Build Auth Scenario sampler group in JMX: POST /auth/login (extract token via JSON Extractor → variable: access_token), POST /auth/refresh at 15-min interval simulation | JMeter | Load | tests/performance/jmeter/TaskFlowPro.jmx | Token refresh |
| PT-JM-03 | Build Project Workflow sampler group: GET /projects (Assert 200 + JSON Schema), POST /projects (Assert 201 + capture project_id), GET /projects/${project_id}/tasks, PUT /projects/${project_id} | JMeter | Load | tests/performance/jmeter/TaskFlowPro.jmx | CRUD chain |
| PT-JM-04 | Build Task Lifecycle sampler group: POST /tasks (capture task_id), PATCH /tasks/${task_id}/status (3 transitions), POST /tasks/${task_id}/comments, DELETE /tasks/${task_id} | JMeter | Load | tests/performance/jmeter/TaskFlowPro.jmx | Full lifecycle |
| PT-JM-05 | Configure JMeter load profile: ramp 50→300 threads over 5 min, hold 10 min, ramp down 2 min — add Response Assertion (status 2xx), Duration Assertion (< 500 ms), Throughput Controller | JMeter | Load | tests/performance/jmeter/TaskFlowPro.jmx | 300 threads |
| PT-JM-06 | Create JMeter soak test plan (Soak_24h.jmx): 100 steady threads, 24-hour duration, hourly Summary Report snapshots — detect memory leaks, connection pool exhaustion, log error rate drift over time | JMeter | Soak | tests/performance/jmeter/Soak_24h.jmx | 24-hour run |
| PT-JM-07 | Add JMeter Listeners: Backend Listener → Graphite/InfluxDB (for Grafana), Summary Report, Aggregate Report, Response Time Graph — configure to write to results/jmeter/jtl/ dir | JMeter | Load | tests/performance/jmeter/listeners.jmx (fragment) | Grafana push |
| PT-JM-08 | Create generate-report.sh: invoke jmeter -n -t TaskFlowPro.jmx -l results.jtl then jmeter -g results.jtl -o reports/html — upload HTML report as GitHub Actions artifact | JMeter | Load | tests/performance/jmeter/generate-report.sh | HTML dashboard |
| PT-JM-09 | Add jmeter-ci.yml GitHub Actions workflow: install JMeter 5.6, run headless, fail if Avg > 400 ms or Error% > 1% (parse JTL with jmeter-check-results.sh Bash script) | JMeter | Load | .github/workflows/jmeter-ci.yml | CI gate |
| PT-JM-10 | Create users.csv seed script (generate-test-users.py): registers 200 users via /auth/register API, writes email,password,userId CSV — run once before any JMeter suite | JMeter | Load | tests/performance/jmeter/data/generate-test-users.py | Data setup |

## 7.4  Gatling — High-Concurrency Stress Tests

Gatling's non-blocking engine handles tens of thousands of concurrent connections efficiently. Use it to find the system's breaking point and validate HPA auto-scaling behaviour on EKS.

| # | Task | Tool | Test Type | File / Area | Notes |
| --- | --- | --- | --- | --- | --- |
| PT-GT-01 | Add Gatling Maven plugin (gatling-maven-plugin 4.x) to pom.xml under a <profile id=gatling>; configure simulations directory: src/gatling/simulations/, results to target/gatling/ | Gatling | Stress | pom.xml | Maven profile |
| PT-GT-02 | Create AuthSimulation.scala: feeder from CSV, scenario loginFlow = exec(POST /auth/login → check status 200 → saveAs token) → exec(GET /projects → check P95 < 200 ms). Inject 500 atOnce users. | Gatling | Load | src/gatling/simulations/AuthSimulation.scala | Scala DSL |
| PT-GT-03 | Create TaskBoardStressSimulation.scala: rampUsers(5000) over 10 minutes hitting GET /projects/:id/tasks and PATCH /tasks/:id/status. Threshold: global.responseTime.percentile3 < 800 ms | Gatling | Stress | src/gatling/simulations/TaskBoardStressSimulation.scala | 5 000 VUs |
| PT-GT-04 | Create NotificationFanoutSimulation.scala: 1 000 users each POST /tasks/:id (assign to another user) simultaneously — verify GET /notifications delivers for all 1 000 recipients within 3 s | Gatling | Stress | src/gatling/simulations/NotificationFanoutSimulation.scala | Fan-out |
| PT-GT-05 | Create HpaScalingSimulation.scala: step-load injection — 100 users/min increments — watch Kubernetes HPA scale backend pods from 2→10. Record pod count vs latency via Prometheus timestamps | Gatling | Stress | src/gatling/simulations/HpaScalingSimulation.scala | EKS HPA |
| PT-GT-06 | Create DashboardAggregationSimulation.scala: 2 000 concurrent GET /dashboard/summary — verify PostgreSQL aggregation query does not cause connection pool saturation (HikariCP active < max) | Gatling | Stress | src/gatling/simulations/DashboardAggregationSimulation.scala | DB pool |
| PT-GT-07 | Add global Gatling assertions in each simulation: forAll.failedRequests.percent.lt(2), global.responseTime.percentile3.lt(800), global.requestsPerSec.gt(50) — fail build on violation | Gatling | Stress | All simulation files | Build gate |
| PT-GT-08 | Add gatling-ci.yml GitHub Actions workflow: mvn gatling:test -Pgatling — upload target/gatling/results/** as HTML artifact; add badge to README with last simulation status | Gatling | Stress | .github/workflows/gatling-ci.yml | CI + badge |

## 7.5  Locust (Python) — Stress, Spike & Soak Tests

Locust enables developer-friendly Python scenarios with real-time web UI, custom event hooks, and easy Grafana integration via locust-plugins. Ideal for exploratory testing and long-running soak validation.

| # | Task | Tool | Test Type | File / Area | Notes |
| --- | --- | --- | --- | --- | --- |
| PT-LC-01 | Create requirements.txt: locust>=2.20, locust-plugins>=4, faker, requests — add tests/performance/locust/ directory; add locust to CI Docker image or use pip install step in workflow | Locust | Soak | tests/performance/locust/requirements.txt | Setup |
| PT-LC-02 | Create locustfile.py base: TaskFlowUser(HttpUser) with on_start() login flow (store token in headers), @task weights: browse_projects(3), view_tasks(5), update_status(2), post_comment(1) | Locust | Load | tests/performance/locust/locustfile.py | Weighted tasks |
| PT-LC-03 | Create stress_locustfile.py: inherit TaskFlowUser; override wait_time=between(0.1, 0.5); add @task create_project, delete_task — run headless: locust --headless -u 3000 -r 100 --run-time 10m | Locust | Stress | tests/performance/locust/stress_locustfile.py | 3 000 users |
| PT-LC-04 | Create spike_locustfile.py: use LoadTestShape class with custom tick() returning (users, spawn_rate): 0-60s=200 users, 60-90s=2000 users, 90-150s=200 users — measure recovery metrics | Locust | Spike | tests/performance/locust/spike_locustfile.py | Shape class |
| PT-LC-05 | Create soak_locustfile.py: 150 steady users, 8-hour duration — log percentile snapshots every 30 min to soak_results.csv; add custom event hook to fire alert if P95 drifts > 20% from baseline | Locust | Soak | tests/performance/locust/soak_locustfile.py | 8-hour soak |
| PT-LC-06 | Add Locust Grafana integration via locust-plugins TimescaleListener: locust --config locust.conf — write metrics to TimescaleDB container; import locust-grafana-dashboard.json into Grafana | Locust | Soak | tests/performance/locust/locust.conf | Grafana live |
| PT-LC-07 | Create notification_spike_locustfile.py: StepLoadShape 0→500→2000→500 VUs targeting POST /tasks (bulk assign) + GET /notifications — assert notification unread_count > 0 in response validation | Locust | Spike | tests/performance/locust/notification_spike_locustfile.py | Notif load |
| PT-LC-08 | Add locust-ci.yml GitHub Actions: run headless Locust stress_locustfile.py for 5 min, 500 users — parse locust_stats.csv, fail if Avg > 400 ms or Fail% > 1% using Python csv + sys.exit(1) | Locust | Stress | .github/workflows/locust-ci.yml | CI gate |
| PT-LC-09 | Create db_soak_locustfile.py targeting write-heavy endpoints (bulk task create + comment flood): monitor PostgreSQL metrics via /actuator/prometheus — verify no connection leak after 4-hour run | Locust | Soak | tests/performance/locust/db_soak_locustfile.py | DB leak check |

## 7.6  Test Data Management & Environment Setup

Consistent, pre-seeded data is required for reproducible performance results. All tooling runs against a dedicated perf environment — never production.

| # | Task | File / Area | Notes |
| --- | --- | --- | --- |
| PT-DT-01 | Create seed-perf-data.sql: 50 projects, 500 tasks (mixed status/priority), 1 000 comments, 200 users — run via Flyway perf profile before any test suite; reset between soak runs | db/seed/seed-perf-data.sql | Flyway migrate |
| PT-DT-02 | Create docker-compose.perf.yml: backend + postgres (performance-tuned: shared_buffers=2GB, max_connections=200) + prometheus + grafana — isolated from dev compose | infra/docker/docker-compose.perf.yml | Perf env |
| PT-DT-03 | Write reset-perf-db.sh: truncate test data tables, re-run seed script, verify row counts — called before each JMeter soak or k6 stress run to ensure consistent baseline | scripts/reset-perf-db.sh | Idempotent |
| PT-DT-04 | Configure Spring perf profile (application-perf.yml): enable query logging (slow queries > 200 ms), set HikariCP maximumPoolSize=50, connectionTimeout=5000, leakDetectionThreshold=10000 | resources/application-perf.yml | Pool tuning |
| PT-DT-05 | Create perf-baseline.json: capture baseline metrics (P50, P95, P99, rps, error%) for each endpoint after first passing k6 load run — used by soak drift alerts and regression detection | tests/performance/baselines/perf-baseline.json | Regression gate |

## 7.7  Unified Reporting & Observability

All four tools push metrics to a single Grafana instance for side-by-side comparison. A summary HTML report is generated automatically after each CI run.

| # | Task | File / Area | Notes |
| --- | --- | --- | --- |
| PT-RP-01 | Configure InfluxDB 2.x container in docker-compose.perf.yml as the shared time-series backend — k6 outputs via K6_OUT=influxdb, JMeter via Backend Listener, Locust via TimescaleListener | infra/docker/docker-compose.perf.yml | Unified sink |
| PT-RP-02 | Create Grafana dashboard (perf-overview.json): panels for P50/P95/P99 per endpoint, virtual users over time, error rate, DB connection pool utilisation, JVM heap — importable JSON | monitoring/grafana/dashboards/perf-overview.json | Import JSON |
| PT-RP-03 | Create generate-perf-report.py: reads all tool outputs (k6 JSON, JMeter JTL, Gatling simulation.log, Locust CSV) → produces unified HTML report with pass/fail per threshold | tests/performance/reports/generate-perf-report.py | Unified HTML |
| PT-RP-04 | Add perf-report.yml GitHub Actions workflow: runs after all tool CI jobs complete → calls generate-perf-report.py → uploads perf-report.html artifact → posts summary table as PR comment via gh CLI | .github/workflows/perf-report.yml | PR comment |
| PT-RP-05 | Add performance regression check: compare current run's P95 values against perf-baseline.json — fail if any endpoint degrades > 20% from baseline; post failing endpoints in PR comment | tests/performance/scripts/regression_check.py | Regression CI |

## 7.8  CI/CD Pipeline Integration Map

The table below shows when each tool runs in the GitHub Actions pipeline, what triggers it, and what gates a merge.

| Workflow | Tool | Trigger | Duration | Gate (fail if…) |
| --- | --- | --- | --- | --- |
| k6-smoke | k6 | Every PR | ~2 min | Any threshold breach |
| k6-load | k6 | main merge | ~15 min | P95 > 300 ms or error > 1% |
| jmeter-ci | JMeter | main merge | ~20 min | Avg > 400 ms or error > 1% |
| gatling-ci | Gatling | main merge | ~25 min | P99 > 800 ms or fail > 2% |
| locust-ci | Locust | main merge | ~10 min | Avg > 400 ms or fail > 1% |
| k6-stress | k6 | Weekly (scheduled) | ~30 min | Breaking point < 1 000 VUs |
| k6-spike | k6 | Weekly (scheduled) | ~15 min | Recovery > 30 s |
| locust-soak | Locust | Weekly (scheduled) | 8 hours | P95 drift > 20% baseline |
| jmeter-soak | JMeter | Weekly (scheduled) | 24 hours | Error rate increase over time |
| perf-report | Python | After all tools | ~3 min | Regression > 20% vs baseline |

## 7.9  Phase 7 Task Summary

| Section | Focus | # Tasks | Tool | Test Types |
| --- | --- | --- | --- | --- |
| 7.2 | k6 Load, Stress & Spike | 10 | k6 | Load · Stress · Spike |
| 7.3 | JMeter Load & Soak | 10 | JMeter | Load · Soak |
| 7.4 | Gatling Stress | 8 | Gatling | Stress · Load |
| 7.5 | Locust Stress, Spike & Soak | 9 | Locust | Stress · Spike · Soak |
| 7.6 | Test Data & Environment | 5 | – | All |
| 7.7 | Reporting & Observability | 5 | Python | All |
| – | TOTAL | 47 | 4 tools | All 4 types |

### Definition of Done

- k6 smoke test passes on every PR; load test passes on every main merge with P95 < 300 ms and error rate < 1%

- JMeter load test generates HTML dashboard report; 24-hour soak shows no error rate drift

- Gatling stress simulation identifies the VU breaking point; HPA scaling validated under step load

- Locust spike test measures recovery time < 30 s; 8-hour soak shows no memory leak or connection exhaustion

- Unified Grafana dashboard displays real-time metrics from all four tools during test runs

- Automated regression check fails CI if any endpoint degrades > 20% vs perf-baseline.json

- Seeded test data script is idempotent and resets cleanly before each major test run

- All performance workflows documented in README with run instructions and threshold rationale

# 8.  Master Task Summary

Total estimated tasks across all 7 phases:

| Phase | Focus Area | Backend | Frontend | Other/Perf |
| --- | --- | --- | --- | --- |
| Phase 1 | Foundation & Authentication | 7 | 8 | — |
| Phase 2 | Project Management | 8 | 7 | — |
| Phase 3 | Task Management | 11 | 9 | — |
| Phase 4 | Comments, Notifications, Activity | 10 | 7 | — |
| Phase 5 | Dashboard, Profile & UI Polish | 5 | 13 | — |
| Phase 6 | DevOps, Testing & Monitoring | — | — | 24 |
| Phase 7 | Performance & Load Testing | — | — | 47 |
| TOTAL |  | 41 | 44 | 71 |

156 total tasks  ·  14 weeks  ·  1 backend developer + 1 frontend developer + 1 QA/DevOps engineer recommended

# 9.  Recommended Working Order

Each phase is a dependency of the next. Within a phase, backend tasks should generally precede or run in parallel with the corresponding frontend tasks once APIs are contracted (DTOs agreed). Phase 7 runs after Phase 6 CI/CD is in place — performance tests require a deployed, containerised environment.

- Weeks 1–2  ·  Phase 1: Stand up skeleton, JWT, login/register — deploy to dev environment

- Weeks 3–4  ·  Phase 2: Projects — merge auth + project features into staging

- Weeks 5–6  ·  Phase 3: Tasks — board and list views become demonstrable to stakeholders

- Weeks 7–8  ·  Phase 4: Comments/Notifs/Activity — full collaboration loop usable in beta

- Weeks 9–10 ·  Phase 5: Dashboard + polish — UI-complete; accessibility audit

- Weeks 11–12 · Phase 6: CI/CD + QA + monitoring — production-ready release

- Weeks 13–14 · Phase 7: Performance & Load Testing — all four tools, all four test types; CI thresholds enforced

Immediate next step for Phase 7: start with PT-DT-01 (seed perf data) and PT-K6-01 (k6 smoke test) in parallel. Smoke tests should pass before any stress or soak runs begin.